## Sheet1
PEFAA Diamond Jubilee Projects
Program For E76 Funded Projects
Sub Project 1 - Washroosm Improvements
Male Toilet Block near DO2, Admin Building 1st. Floor Wash rooms
| Time | 2024 | [23 empty] | 2025
|  | July |  |  |  | Aug |  |  |  | Sep |  |  |  | Oct |  |  |  | Nov |  |  |  | Dec |  |  |  | Jan |  |  |  | Feb |  |  |  | March |  |  |  | April
| Activity | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
1 | Work Identification and Proposal Preparation
2 | Budgeting
3 | Material lists and Supplier identification
4 | Bid Invitation and evaluation
5 | Negotiations and finalization of items
6 | Labour Contractors identifications and Bid Preparation
7 | Supply award
8 | Labour contract Award
9 | Delivery of Material
10 | Work start at site
11 | Work completion
Sub Project 1 - Washroosm Modification
Male Toilet near DO2, Admin Building 1st. Floor Wash rooms
| 1 | July 4: Work Identification and Proposal Preparation; Dec 4: July and August 2024
| 2 | July 4: Budgeting; Dec 4: Sepetmber and October 2024
| 3 | July 4: Materrial lists and Supplier identification; Dec 4: Novemebtr 2024
| 4 | July 4: Bid Invitation and evaluation; Dec 4: 2024-12-01
| 5 | July 4: negotiations and finalization of irems; Dec 4: 2025-01-01
| 6 | July 4: Supply award; Dec 4: Feb first week
| 7 | July 4: Delivery of Material; Dec 4: Feb 3rd. Week
| 8 | July 4: Labour Contractors identificationa and Bid Preparation; Dec 4: 2025-01-01
| 9 | July 4: Labour contract Award; Dec 4: Feb 2nd week
| 10 | July 4: Work start at site; Dec 4: 1st. March 2024
| 11 | July 4: Work completion; Dec 4: 20th. April 2024